## REPAIRS
LOS OLIVOS IWDD #1 REPAIRS
UPDATED 3/15/25
Reviewed w/ Contractor | Address | Description and diagnosis | Quoted Cost | Final Cost | Status | Repair Date
| 2217 N. Alvarado | Need back yard valve replaced. | 450 | 148 | Repaired | 2020-08-13
2021-08-21 | 124 E. Palm | Need front yard valve replaced. | 1000 | 1510.14 | Repaired | 2021-09-24
2020-08-21 | 349 E. Monte Vista | Ron Kilgard property- no water in backyard. Valve likely needs to be connected to line. | 1560 | 1558.68 | Repaired | 2020-08-25
| 375 E. Alvarado | Raise Irrigation Box to prevent future flooding of neighbro property. | 900 | 838.3 | Repaired | 2020-09-28
| 2016 N. Alvarado | Valve was replaced but gate needs to be added to control flow to valve from outside property. | 700 | 878.97 | Repaired | 2020-09-24
2020-08-21 | 360 Palm Lane | Casey Family Program Yard. Pipe broken at NW corner near valve. | 750 |  | Repaired | 2020-09-24
2021-10-30 | 341 E. Monte Vista | Pipe Replacement near valve |  | 589.34 | Repaired | 2020-10-30
2020-08-21 | Heard Museum 2222 N. Alvarado? | Heard Museum gates at NE corner of parking lot. Grate cover requires reinforcement at standbox on grade | 3000 | 2765.34 | Repaired | 2020-08-21
2020-11-14 | 119 E. Alvarado | Lateral line leak | 500 | 449.97 | Repaired | 2020-11-14
2020-11-14 | 2233 N. Alvarado | Both front yard valves leak and pipe under driveway. | 1100 | 1065.93 | Repaired | 2020-11-14
2020-11-15 | 2233 N. Alvarado | Both front yard valves leak and pipe under driveway. Additional repair |  | 399.97 | Repaired | 2020-11-16
2020-11-30 | 2026 N. 3rd. St. | New HDPG required | 1283.74 | 1283.74 | Repaired | 2020-02-03
2020-11-30 | 374 E. Monte Vista | Large Leak on back lateral line. Needs sawcutting of pavement to complete repair. | 2922.49 | 2922.49 | Repaired | 2021-02-05
2020-11-30 | 389 #. Palm | Leaking Standbox. Reset and Reseal | 449.97 | 449.97 | Repaired | 2021-02-05
2020-11-30 | 73 E. Monte Vista | Broken lateral line. Small leak repair. | 449.97 | 449.97 | Repaired | 2021-02-05
2020-11-30 | 360 E. Palm | Casey Family. Large leak repair. | 449.97 | 449.97 | Repaired | 2021-02-05
| 500 E. Coronado Rd. | 7th St and Alleyway between Coronado and Palm. Lateral crack and leak at standbox at NE corner. Saw cut asphalt and remove 15'x12" laterally cracked concrete pipe. Install 15'x12" 80 # PIP using proper adaptations and bonding material. Deliver 1/2 sack slurry to backfill trench. Deliver road plates to cover trench. Patch back saw cut asphalt. This repair delayed due to availability of asphalt & concrete. | 5/11/22 New quote: $10,222.50 actual repair cost was $4491.50 due to slip lining the pipe | $225 for temporary repair on 4/13/21 $4491.50 | Repaired | 2023-01-12
2021-03-01 | 340 E. Monte Vista | 340 E Monte Vista. Front yard broken valve. |  |  | Repaired | 2021-04-13
2021-06-16 | 112 E. Alvarado | Broken lateral at corner of yard at street |  |  | Approved
2021-06-17 | 371 E. Monte Vista | Broken pipe next to the NW valve in the front yard. |  |  | Approved
2021-06-16 | 3rd & Alvarado | Large box at 3rd st. and Alvarado has the gate going south that won't hold water well. |  | 700.5 | Repaired | 2022-01-04
2021-08-03 | 2233 N. Alvarado | Broken pipe at the corner of Alvarado and Alvarado at the house on the SE corner. |  | 450 | Repaired | 2021-08-23
2021-08-03 | 390 E. Monte Vista | Gate that goes to the back of the yard is leaking. Box is the one that is adjacent to lawyers parking lot on 7th st. |  |  | Approved but reevaluating fix.
2021-08-13 | 360 E. Mone Vista | Break in the round stand box in the NW corner of the backyard. South gate lever has separated from the square plate that blocks the opening in the box. |  | 509.87 | Temp emerg. Repair completed. Final repair Approved. | 2021-08-23
2021-09-24 | between 2238 & 2242 N. Alvarado | Blockage in Line. Will need to jet clean line. | 2000 | 1685 | Repaired | 2022-03-22
2021-11-22 | 2233 N Alvarado | Standbox cover rusted away | 450 | 375.5 | Repaired | 2022-03-22
2021-11-22 | 380 E Monte Vista | South gate from lateral has broken away from box. |  |  | Emerg. $250 repair completed. Awaiting permanent fix
2021-11-22 | 349 E Monte Vista | Broken standbox rebuild. |  | 496.5 | Repaired | 2022-01-04
2021-11-22 | 105 E Palm Lane | Potential new valves for Palm Lane Gardens |  |  | Investigated by district. Repair to be paid by property.
| 56 E. Palm Lane | Installed new valve lid with new valve stem |  | 175 | Repaired | 2022-03-22
2022-05-03 | 124 E. Palm Lane | Broken pipe on front yard, 3’ north of front yard valve. This repair was also done last August due to cars/trucks driving over the pipe. Valve should be moved out of path of traffic prior to this repair being done again. | $500 (initial quote) New Quote: $3,254.00 approved at 6/25/22 mtg. | 3254 | Repaired | 2022-05-24
2022-05-03 | 134 E. Palm Lane | Broken pipe against fence caving in laterally. Leaks but not an emergency or affecting neighbors getting their water. Reviewed by Nate. **Repair is on hold at the request of property owner Bob Hurley. He will be in CA for a month and needs time to have his yard crew clear out the brush in the back. | $500 (initial quote) **Update: Actual cost will be $16,747 | 13070 | Repaired | 2022-11-21
5/3/2022 New Issue 5/11/22 | 357 E. Monte Vista | Broken line on northwest corner of property causing huge bubble in lawn when line is charged. New issue: Driveway crack in concrete is leaking. Need to excavate & expose main line to repair and replace concrete. Work will be scheduled either week of 8/1 or 8/15. | $500 initial quote. New issue quote: $3633.50 -driveway rep $3,000 | -$2202 for 1st issue - 2nd issue $3274.50 -3rd issue $3,000 | Repaired | 1st issue on 6/14/22 2nd issue on 9/12/22 3rd issue on 10/3/22
2022-05-03 | 2230 N. Alvarado | Need to have winglets welded on to the backyard valve so that the gate can be tightened down and opened up with proper tool. **Update: Nate will determine valve stem size needed and then give quote for new valve cover. | 750 | 711.5 | Repaired | 2022-06-14
2022-05-03 | 51 E. Monte Vista | Need to demo and remove stand-box at NW corner. Excavate and expose main irrigation line. Install 10’-15’ x 12”80#PIP service line with 12” valve to area just west of 51 E. Monte Vista. Install new 6” service line with 6” valve to W property line. Pour new splash pad and construct new headwall around 6” valve. Deliver fill dirt to construct berm and fill void in area of stand box. | 3154.1 | 3336.6 | Repaired | 2022-05-04
| 375 E. Alvarado | The southbound slide gate that feeds water into the back yard of 380 E. Monte Vista is extremely loose. Temporary repair was done but it may need a more expensive build out. This repair is tabled until we have more information. **Update: This was completed in January. Nate determined a longer handle is needed for the gate to secure in place and will cost $45. | $2000 (initial quote) **Update: Actual cost $750 | 750 | Repaired | 2022-01-11
2022-05-03 | 131 E. Alvarado (Pansing) | Stand box at N/E corner: remove deficient S-bound pipe gate from stand-box. Install new 15" galvanized waterman c10 pipe gate. Stand box at S/E corner needs to be replaced. **Update: Gate for N/E corner stand box has been ordered. Nate will complete this repair when it arrives. Awaiting revised bid to reflect total rebuild of S/E corner stand box. | $2013.5 for repair on N/E corner box; New quote for stand box at S/E corner $6063 | 2013.50 pd on 10/4/22 $6063.00 on 11/21/22 | Repaired | 10/4/22 and 11/11/22
2022-05-03 | 2026 N. 3rd. St. (Contreras) | Stand box lid has hinge that needs to be spot welded. Nate will take the cover to Fuller Form to have them repair. There will be no cost. | 0 |  | Repaired | 2022-06-27
2022-05-11 | 65 E. Monte Vista Rd. (Zugor) | Need 2 6" valves replaced. | 791.5 |  | Repaired | 2022-06-27
2022-06-25 | 363 E. Palm Lane AKA 378 E. Palm Lane | Major fractures in stand box. Need to replace. **Update: Awaiting revised bid to reflect the total rebuild of stand box. | $5100 done on 2/11/23 2nd issue repaired for $550 on 2/17/23 | 5650 | Approved at 6/25/22 mtg. | 2/11/23 and 2/17/23
2022-05-11 | 2021 N. Alvarado | Hand dig & expose valve riser adjacent to bougainvilla. Remove deficient valve & cap riser at main | 564.5 |  | Repaired | 2022-06-27
2022-05-11 | 56 E. Palm Lane | Remove deficient gasket from valve lid and install new 10" gasket. | 170 |  | Approved at 6/25/22 mtg.
| 371 E. Monte Vista | Reset displaced irrigation valve, this was an emergency repair. |  | 450 | Repaired | 2022-11-01
2024-01-15 | 389 E. Palm Lane | 1. Resealed stand box location at S/E corner of the lot in alley. 2. Demo & remove stand box, saw cut and remove 10x23 concrete pipe. Install 12-15'x12" 80#PIP using proper adaptations and bonding material. | 1. $421.00 2. $2866.50 | 3287.5 | Repaired | 1/23/2024 & 2/19/24
2024-01-15 | 357 E. Monte Vista | Repair broken joint/ring crack. Reset pipe and backfill. | 600 | 600 | Repaired | 2024-01-23
2024-01-15 | 360 E. Monte Vista | Replaced old toggle gates with new gates and 3’ handle extensions. | 1041.5 | 1041.5 | Repaired | 2024-01-24
2024-01-15 | 124 E. Palm Lane | Replaced deficient gate from stand box and installed new gate with handle extension | 789.5 | 789.5 | Repaired | 2024-01-24
2024-01-31 | 371 E. Monte Vista | Replaced valve stem. | 150 | 150 | Repaired | 2024-02-01
2024-02-03 | 2024 N 7th St. | Remove 2x pipe gates from standbox. Install 2x new 10"x5' HDPD using concrete anchors and hydraulic rapid set. | 2740 | 2740 | Repaired | 2024-02-19
2024-04-12 | 2034 N. 3rd St. | Repair broken joint/ring crack. Reset pipe and backfill. | 600 | 600 | Repaired | 2024-04-12
2024-04-22 | 2016 N. Alvarado | Repair broken joint/ring crack. Reset pipe and backfill. | 600 | 600 | Repaired | 2024-04-22
|  | Irrigation line that runs parallel to the Heard Museum feeding homes on Alvarado has blockage and needs to be hydro jetted. | 2500
2024-07-24 | 2242 N. Alvarado | Hydro Jet main irrigation line located at N/W corner of prop. | 900 | 900 | Repaired | 2024-07-24
2024-08-28 | 2242 N. Alvarado | Escavate and expose main irr. Line. Saw cut pipe and remove lg root ball. Reset and backfill. | 800 | 800 | Repaired | 2024-08-28
2025-01-14 | 3rd & Alvarado | Replace W bound gate slide, tension bar, guide plate & bolts. | 460 | 460 | Repaired | 2025-01-14
2025-02-12 | Heard Museum | Heard M. stand box: Remove irr gates & screen cover from irr stand box as needed. Demo * remove top two courses of stand-box. Install 10"80#PIP into stand-box & connect to inlet & 2x outlet pipes with proper adaptations & bonding material. Deliver fill dirt & backfill. | 4030 | 4030 | Repaired | 2025-02-12
2025-03-12 | 363 E Monte Vista | Install new complete valve assembly. | 650 | 650 | Repaired | 2025-03-12